____1.	Staff lead. (Due July 20)

One person is appointed by the vice president and/or unit administrator to serve as the staff lead throughout the review process.  This individual will supply his/her name and contact information to the provost’s executive assistant no later than July 20.  The staff lead will be responsible for communications to and from the Office of the Provost regarding the SUR process and updates.

____2.	Self-study group. (Due August 1)

Depending on the size of the department, it may be appropriate to appoint 1-2 additional individuals to assist the staff lead with the self-study phase of the review. The group would work with other departmental staff in obtaining the information and drafting the self study.

____3.	Vice president identifies special issues. (If chosen to submit, due August 1)

In accordance with the SUR Policy, Section III.7, each vice president may develop a set of topics that are timely and unique for issues facing the unit under review. These topics should be submitted to the staff lead no later than August 1.

____4.	Select members for the phase 2 external review team. Use form on page 1.8 (Due August 27)

In phase 2, a review team comprised of 3 to 5 individuals from outside the unit and the internal self-study group will conduct a review.  The team should be representative of those that the unit serves and may consist of faculty, staff, and students, and when appropriate, from outside the university.

The staff lead, in consultation with the vice president, selects individuals to serve as the external review team, completes the form on page 1.8, and submits the form to the provost’s executive assistant no later than August 27.  The provost’s executive assistant will submit the faculty names for all departments undergoing support unit review to the Committee on Committees for approval by December 1.

____5.	Institutional research data and/or department surveys.

The Office of Institutional Research can provide institutional research data upon the request of the department.  If none is available, or if supplemental information is needed, Institutional Research may assist with the development and/or administration of a campus-developed survey.  For more information, please contact the Office of Institutional Research at x3281.

____6.	Self-study report.  Use form on pages 1.6-1.7. (To be completed by December 1)

Follow the self study instructions beginning on page 1.1 to complete the self-study report  found on pages 1.6-1.7.  Information gleaned from institutional research data and/or departmental surveys, departmental meetings/interviews, and other resources should be included.  This document will be the primary information resource for the external review team.

Regardless of the evaluation tool being used, the special issues discussed on page 1.4, item 7 of this form must be addressed and included in the department’s self-study report.

To assist the self-study group, possible questions have been included in various sections.

Blue Questions  These are questions that the internal self-study group could use to elicit more information from members of their department.

Red Questions  These questions are required as special issues specific to this year’s SUR cycle.  Again, information is obtained from members inside the department.